## Functionalities
Ecommerce Application Functionalities
TEAM : Ayushi, Shravya , Mayank, Ekta
Users can be :
| 1)customer | Functionalities
Register into system
login into system
view, add and remove products from shopping cart
place order, view previous placed orders
cancel order
payment
filter products
track/enquiry order
claim refund
View and update customer Profile
update order
| 2)Admin | Functionalities
Login
Product Management (CRUD Operation)
Customers Management
Orders Management
Add discount
block user/seller
Add product Category
| 3)Visitor | Functionalities
View Products
Adding products to cart
Register to website
Chat(using CHAT-BOX)
HomePage functions
| Main App: | Home screen
Login / Logout/ Signup
Product Catergory List (mat side nav to be moved to home component)
Filter products as per category/price/gender
Contact Us (Router Link mapping remaining)
About Us (Router mapping remaining)
Database Used
| Database Used | MySql
| Tables | Product details
Orders summary
Customers Details
Order details
Categories can be :
Main categories :
Electronic
clothing
accesories
books
Bags and Luggage
Footwear
Make-up

## Changes&Recommendations
Changes & Recommedations section
More Features which needs to be implemented |  | status
1)Customer should be able to remove products from cart
2) Add category Table |  | completed
3)Product Return Module
4)Pagination on home page for items
5) filter by => category, price,band, rating ,release Date (checkbox -multiple filtering of products
6)Remove Status ==> Approve/Pending from user and admin
7)Manufacturing Date field for Product
8)Discount field while adding product -Admin
9) admin should be able to add category
10)customer management under Admin
11)Chat Box
Drawbacks and faults in current Version |  | status
2) if I close the tab and reopen it again then session ends hence cart Items vanishes. these 3 soln's are possible:
a)Store data in Cookies and reinitialize the Session Model if it’s null.
b) Fetch data at runtime from API with help of JWT token and reinitialize the Session Model if it’s null
c) or save cart in database
3)product image implementation |  | working on this
4) page rerendering where we have used window reload : in remove products from admin and update order status
2nd release

## FrontEnd-taskFlow
FrontEnd developers : ayushi and mayank Angular framework used
Modules |  |  | Routes | Task Status
| 1)Home Module |  | /home | completed
|  | Banner component | no route (included in layout)
|  | Home Component | no route(included in layout)
|  | Profile | /home/profile
|  | update-profile | /home/update
| 2)Product module |  |  | Completed
|  | product-item | no route (included in home)
|  | Product-list | no route (included in home)
| 3)Shared module |  |  | Completed
|  | footer component | no route (included in layout)
|  | Header component | no route (included in layout)
|  | About-us | /info/about
|  | Contact-us | /info/contact
| 4)auth module |  | /auth | Completed
|  | Customer_login component | /auth/login
|  | register | /auth/register
|  | Admin_login | /auth/logByAdmin
| 5)Admin module |  | /admin | completed
|  | add-category | /admin/addcategory
|  | add-product | /admin/addproduct
|  | admin header | no route(included in admin home)
|  | admin Home | /admin/home
|  | edit-product | /admin/editproduct/:product_id
|  | product-cart | no route(included in admin home)
|  | product-detail | /admin/productdetail/:product_id
|  | order-list | /admin/orderlist
|  | order-detail | /admin/orderdetails/:id
| 6)Order module |  | /cart | Completed
|  | cart | no route(included in checkout)
|  | checkout | /cart/checkout
|  | order-return-details | /cart/previousdetails
|  | order-returns | /cart/previous
|  | show-cart | /cart/show
|  | success-order | cart/success/:id
| 7)App(main) module | App component | no route deafult ' ' for customer | completed
layout component
| 8) Material Module |  | for using angular material | completed
Core
| 1)Models :- |  |  | completed
|  | Customer | customerId, customerName, email, password, address , phno, delivery address
|  | Order | orderid, customerid , status ,total_amount
|  | Products | product_id , product_name, total_quantity, description,category,product_price,product_image
| 2)Services (AT FRONTEND) | customer service | server side port :9595 | completed
|  | product service | server side port :5555
|  | order service | server side port :9999
|  | admin service | server side port :5959
cart service
messenger service
Drawbacks for now(removed)
| profile visible if email session value is null then also |  | solved
| admin login is taking email and pass as obj in server side |  | solved
| In admin router , routing with parameters not happening |  | solved
| Logout button to be disable when email session is null |  | solved

## Tables
Database : ecommerce
Customers
customerId | customerName | email | password | address | phno | delivery_address
autogenrated-int | string | string | string | string | long | string
Orders
orderid | customerid | status |  |  | total_amount
auto-id | fron user table | String mayank(Ordered) Ekta(delivered,shipped) |  |  | int
order_details
order_id | product_id | quantity
from order table | from prod table | number
Products
product_id | product_name | total_quantity | description | Product Image | category | product_price
auto-id | string | int | string | blob | string | int
INSERT INTO `product`(product_id,product_name,total_quantity,description,category,product_price) VALUES (1,"Iphone",100, "cell phone for use sample description","electronics",80000);
Category
categoryId | categoryName
String | String
add more fiellds as date mfg, discount in product table
introduce category table

## BackEnd-Service&Controllers
BackEnd Developers : Shravya and Ekta SpringBoot used for microservices
Services
|  |  | controllers | Assigned To | Status
1 | Customer:
port:9595
|  | login : | https://localhost:9595/customer/login/email/password (values by jsonbody) | Shravya | completed
|  | Register: | https://localhost:9595/customer/register (values by json) | Shravya | completed
|  | update profile | https://localhost:9595/customer/update (values by json) | shravya | completed
|  | update password | https://localhost:9595/customers/forgot/{email} (value by url) | Shravya | completed
|  | get customer by email | https:localhost:9595/customers/bymal/{email} (returns the json obj) | Shravya | completed
|  | show customers | https://localhost:9595/customer/show | Shravya | completed
|  | delete customer | https://localhost:9595/customer/remove/customerid (values by url) | Shravya | completed
2 | Orders
| port:8080 | saveorder & return orderid | https://localhost:9999/orders/save (values by json) | Shravya | Completed
|  | Show Orders | https://localhost:9999/orders/show | Shravya | Completed
|  | Show orderbyid | https://localhost:9999/orders/showorder/{orderid} (value by url) | Shravya | Completed
|  | Update order (only status) | https://localhost:9999/orders/save (order id by url, body by json) admin control | Shravya | Completed
|  | Delete order | https://localhost:9999/orders/remove/{orderid} (values by url) admin control | Shravya | Completed
3 | Order Details
|  | Save Order Details | orderDetails/save(order_id,product_id,product_quantity)
4 | Product Details
| port:5555 | show product | http://localhost:5555/products | Ekta | completed
|  | show product by id | http://localhost:5555/products/{id} | Ekta | completed
|  | save product | http://localhost:5555/products | Ekta | completed
|  | update product | http://localhost:5555/products/{id} | Ekta | completed
|  | delete product | http://localhost:5555/products/{id} | Ekta | completed
|  | save category | https://localhost:5555/products/save/{category} (value by json)
|  | get category | https://localhost:5555/products/search/{categoryid} (value by url)
|  | Image implement |  | Ekta | completed
5 | Admin
| port:5959 | login | localhost:5959/admin/login/admin@gmail.com/admin | Ekta | completed
|  | show all customers | localhost:5959/admin/users | Ekta | completed
|  | show all products | localhost:5959/admin/products | Ekta | completed
show all orders
show order by id
remove products by id
remove customers by id
update products by id
add products
get product by id
get customer by id
add category

## Flow
Register -- > login --> Show product -->Add product -->